## Example
RACI Chart (Roles and Responsibilities Matrix)
Nom du Projet | Work'in Share , Général du projet
Commencé le | 2018-02-05 | Revision: | 2018-02-05
Commentaires | R - Responsible - il réalise A - Accountable - il supervise et rend des comptes C - Consulted - il conseille I - Informated - il est informé
TRAVAIL | Jonathan | Killian | Kenji | Client | Prestataire
ANALYSE DU CACHIER DES CHARGES | IC | R | AR | I | IC
Chiffrage financier | IC | R | AR | I | IC
Analyse du Besoin | IC | R | AR | I | IC
Mise a jour du cahier des charges | IC | R | AR | I | IC
Charte graphiques du site web | IC | R | AR | I | IC
Creation et mise a jour du diagramme de Gantz | IC | AR | R | I | IC
creations des matrices RACI | AR | R | R | I | IC
APPLICATION C | AR | IC | IC | I | IC
Application QRCODE | AR | I | I | I | IC
Application de sortie/entrée XML | AR | I | I | I | IC
DEVELOPPEMENT WEB | IC | AR | R | I | IC
MCD ET MLD | R | A | IC | I | IC
Mise en place de la base de donnée | IC | AR | R | I | IC
Choix du template | IC | A | R | I | IC
Html / Css | IC | AR | R | I | IC
Developpement Dynamique | IC | AR | R | I | IC
RESEAU | R | IC | AR | I | IC
,,,, | - | - | - | I | IC
,,,, | - | - | - | I | IC
R = Responsible, A = Accountable, C = Consulted, I = Informed

## Blank RACI
RACI Chart (Roles and Responsibilities Matrix)
For instructions / training material visit http://www.racichart.org
Process Name / Description: | Describe the process that this RACI addresses
Created On: | Date | Revision: | Date last revised
Created by: | Note all team members/functions who developed and agreed to this RACI
| Function A | Function B | Function C | Function D | Function E
First Responsibility
Second…
Third…
Fourth…
Fifth…
Sixth…
R = Responsible, A = Accountable, C = Consulted, I = Informed
© 2012 racichart.org