## Example
RACI Chart (Roles and Responsibilities Matrix)
Nom du Projet | Work'in Share , partie réseau mission 3
Commencé le | 2018-02-05 | Revision: | 2018-02-05
Commentaires | R - Responsible - il réalise A - Accountable - il supervise et rend des comptes C - Consulted - il conseille I - Informated - il est informé
TRAVAIL | Jonathan | Killian | Kenji | Client | Prestataire
ETUDE | IC | R | AR | I | IC
Etude du cahier des charges existant | IC | R | AR | I | IC
Etude du besoin du client | IC | R | AR | I | IC
Validation du nouveau cahier des charges | IC | R | AR | I | IC
MATERIEL | IC | AR | R | I | IC
Etudes des cables dont on aura besoin | IC | AR | R | I | IC
Recherche Fournisseur materiel | IC | AR | R | I | IC
Etude Commercial et Depenses | IC | AR | R | I | IC
Selection du Fournisseur materiel | IC | AR | R | I | IC
CONFIGURATION | AR | IC | R | I | IC
Configuration des routeurs | AR | IC | R | I | IC
Configuration des ACL | AR | IC | R | I | IC
Configuration IP | AR | IC | R | I | IC
DEPLOIEMENT | R | IC | AR | I | IC
Installation des infrastructures | R | IC | AR | I | IC
Deploiement automatisé | R | IC | AR | I | IC
RECETTE | IC | AR | R | I | IC
Cout du service | IC | AR | R | I | IC
Benefice etc.. | IC | AR | R | I | IC
R = Responsible, A = Accountable, C = Consulted, I = Informed

## Blank RACI
RACI Chart (Roles and Responsibilities Matrix)
For instructions / training material visit http://www.racichart.org
Process Name / Description: | Describe the process that this RACI addresses
Created On: | Date | Revision: | Date last revised
Created by: | Note all team members/functions who developed and agreed to this RACI
| Function A | Function B | Function C | Function D | Function E
First Responsibility
Second…
Third…
Fourth…
Fifth…
Sixth…
R = Responsible, A = Accountable, C = Consulted, I = Informed
© 2012 racichart.org